# Healthcare Utilization and 30-Day Hospital Readmission Analysis for Diabetic Patients

# 1.Project Overview:

This project aims to analyse healthcare utilization and identify factors associated with hospital readmission within 30 days among diabetic patients. The analysis will use the publicly available Diabetes 130-US Hospitals dataset from the UCI Machine Learning Repository. The project will examine patient demographics, hospital admission details, previous healthcare utilization, diagnoses, medications, and other available factors to understand their relationship with 30-day readmission.

# 2. Problem Statement:

Hospital readmission is an important healthcare outcome because repeated hospital visits can increase healthcare costs and indicate that patients may require additional care or follow-up. This project will examine the factors associated with readmission within 30 days among diabetic patients. The analysis will focus on understanding patterns in patient characteristics, hospital stay, previous healthcare utilization, diagnoses, and medications that may be related to 30-day readmission.

# 3. Project Objective:

The main objective of this project is to analyse healthcare data and identify factors associated with hospital readmission within 30 days among diabetic patients.

## Specific Objectives:

- Analyse the 30-day readmission rate among diabetic patients.

- Examine the relationship between patient characteristics and readmission.

- Analyse the relationship between hospital stay and readmission.

- Examine previous inpatient, emergency, and outpatient visits.

- Identify important factors associated with 30-day readmission.

- Identify data-quality and missing-value issues.

# 4. Research Questions:

- What percentage of diabetic patients are readmitted within 30 days?

- Which patient characteristics are associated with 30-day readmission?

- Is length of hospital stay related to readmission?

- Is previous hospital utilization related to readmission?

- Which factors appear to be most important for 30-day readmission?

# 5. Data Source:

The primary dataset for this project is the Diabetes 130-US Hospitals dataset obtained from the UCI Machine Learning Repository. The dataset contains hospital encounter information for diabetic patients, including demographic details, admission information, diagnoses, medications, laboratory procedures, and previous healthcare utilization. The dataset also contains the readmission outcome, which will be used to identify patients readmitted within 30 days.

## 5.1 Dataset Details:

- Dataset: Diabetes 130-US Hospitals

- Source: UCI Machine Learning Repository

- Records: 101,766 hospital encounters

- Variables: 50 columns

- Main outcome: readmitted

- 30-day readmission value: <30

- Other outcome values: >30 and NO

## 5.2 Key Variables:

- Age: Patient age group.

- Gender: Patient gender.

- Race: Patient race category.

- Time in hospital: Number of days spent in the hospital.

- Number of diagnoses: Number of diagnoses recorded.

- Number of medications: Number of medications used.

- Number of inpatient visits: Previous inpatient visits.

- Number of emergency visits: Previous emergency visits.

- Number of outpatient visits: Previous outpatient visits.

- Readmitted: Indicates whether the patient was readmitted.

# 6. Key Healthcare Metrics:

- 30-day readmission rate: Percentage of patients readmitted within 30 days.

- Average length of stay: Average number of days patients stay in the hospital.

- Previous inpatient visits: Number of inpatient visits before the current admission.

- Previous emergency visits: Number of emergency visits before the current admission.

- Previous outpatient visits: Number of outpatient visits before the current admission.

- Number of medications: Number of medications recorded during the hospital encounter.

# 7. Literature Review:

Previous research has shown that hospital readmission can be influenced by several factors, including patient characteristics, previous healthcare utilization, medical conditions, medications, and information recorded during hospitalization. Studies have also used statistical and machine learning methods to identify patients at higher risk of readmission. This project will build on these findings by examining similar factors in the Diabetes 130-US Hospitals dataset and focusing specifically on 30-day readmission.

# 8. Planned Methodology:

- Understand the dataset and its variables.

- Check the data for missing values and inconsistencies.

- Prepare the data for analysis.

- Analyse patient and hospital characteristics.

- Compare patients who were readmitted within 30 days with other patients.

- Identify factors associated with 30-day readmission.

- Summarize the findings and limitations.

# 9. Data Collection Strategy:

The primary data for this project has been obtained from the publicly available UCI Machine Learning Repository. The downloaded files, “diabetic_data.csv” and “IDS_mapping.csv”, will be stored in the “Raw_Data” folder without modification. The original data will be preserved, and any cleaning or transformation will be performed on a separate working copy during the analysis stage.

# 10. Tools and Resources:

- Microsoft Excel: Planned for initial data review and basic analysis.

- SQL: Planned for querying and aggregating healthcare data.

- Python: May be used for advanced analysis if required.

- Microsoft Word: Used for project documentation.

- UCI Machine Learning Repository: Used as the primary data source.

# 11. Ethical Considerations:

- The project will use publicly available healthcare data.

- Individual patients will not be identified or contacted.

- Patient information will not be shared outside the project.

- Sensitive variables such as age, gender, and race will be handled responsibly.

- Results will be reported in an aggregated manner where appropriate.

- The analysis will identify associations and will not claim that a factor directly causes readmission.

- The results will be used for educational and analytical purposes, not for making clinical decisions.

# 12. Risk Assessment and Contingency Plan:

| Risk | Possible Impact | Contingency Plan |
| --- | --- | --- |
| Missing data | May affect the accuracy of the analysis | Identify missing values and document an appropriate handling method |
| Incorrect or inconsistent data | May affect the quality of the results | Check values and document necessary corrections |
| Limited project time | Some planned analysis may not be completed | Prioritize the main analysis and required deliverables |
| Dataset limitations | Results may not represent all hospitals or countries | Clearly state the limitations in the final report |
| Imbalance readmission outcomes | May affect analysis and future modelling | Report the outcome distribution and use appropriate evaluation methods |
| Privacy or ethical concerns | Healthcare data may contain sensitive information | Use only the public dataset and avoid identifying individuals |

# 13. Project Timeline:

| Week | Dates | Activities | Deliverables |
| --- | --- | --- | --- |
| Week 1 | 04-Aug-2026 to 10-Aug-2026 | Project planning, literature review, dataset selection | Project plan |
| Week 2 | 11-Aug-2026 to 17-Aug-2026 | Data collection, data understanding, data cleaning | Cleaned dataset and data-quality notes |
| Week 3 | 18-Aug-2026 to 24-Aug-2026 | Exploratory data analysis and descriptive analysis | Analysis results |
| Week 4 | 25-Aug-2026 to 31-Aug-2026 | Identify important factors and perform planned analysis | Analytical findings |
| Week 5 | 01-Sep-2026 to 08-Sep-2026 | Final interpretation, documentation, and presentation | Final report and presentation |

# 14. Expected Outcomes:

This project is expected to provide an understanding of the factors associated with 30-day hospital readmission among diabetic patients. The project will also produce a structured data-analysis workflow, identify important healthcare metrics, highlight data-quality issues, and provide findings that may support future healthcare analytics studies.

# 15. Project Limitations:

- The dataset contains historical healthcare data and may not represent current healthcare practices.

- The dataset represents US hospitals and may not be directly applicable to other countries.

- Missing or incomplete information may affect the analysis.

- The analysis can identify associations but cannot prove causation.

- The project is intended for educational and analytical purposes and not for clinical decision-making.

# 16. References:

- UCI Machine Learning Repository. Diabetes 130-US Hospitals for Years 1999–2008.
https://archive.ics.uci.edu/dataset/296/diabetes+130-us+hospitals+for+years+1999-2008

- Artetxe, A., Beristain, A., & Graña, M. Predictive models for hospital readmission risk: A systematic review of methods.

- Zhou, H., et al. Systematic review of models for predicting hospital readmission.

- U.S. Department of Health & Human Services. HIPAA De-identification Guidance.
https://www.hhs.gov/hipaa/for-professionals/special-topics/de-identification/index.html